## Sheet1
Defect ID | Assigned To Name | Date Raised | Defect Category | Defect Severity | Defect Status | Environment | Raised By Name | Summary
66 | Gan Kim Aun | 2019-10-07 | Program Error | 1-Critical | WIP | UAT | Ong Yei Ling | Missing QFPay Merchant and Terminal reports after process Cardlink file
67 | Gan Kim Aun | 2019-10-07 | Data Error (Conversion) | 1-Critical | WIP | UAT | Ong Yei Ling | Missing Alipay Online Merchant Registration reports from QFPay after processed merchant and terminal files
71 | Gan Kim Aun | 2019-10-08 | Data Error (Conversion) | 3-Medium | WIP | UAT | Ong Yei Ling | GHL QR Sales & Pre-Auth - Show Wallet label when display QR code on screen
72 | Gan Kim Aun | 2019-10-08 | Data Error (Conversion) | 3-Medium | WIP | UAT | Ong Yei Ling | GHL QR Sales and Pre-Auth - Remove E6-1145 on screen when auto inquiry
75 | Gan Kim Aun | 2019-10-09 | Data Error (Conversion) | 2-High | Reopen | UAT | Lum Wai Kuan | QR void failed for Pre-Auth transaction with error "INVALID TXN INPUT"
73 | Gan Kim Aun | 2019-10-09 | Data Error (Conversion) | 2-High | Open | UAT | Ong Yei Ling | Invalid Merchant Info Registered to QFPay
79 | Gan Kim Aun | 2019-10-09 | Data Error (Conversion) | 2-High | Open | UAT | Ong Yei Ling | Alipay Void of Sales TRANS ID not match with receipt
85 | Gan Kim Aun | 2019-10-10 | Program Error | 2-High | Open | SIT | Roma Lledo | Merchant Settle File Issues from QFPAY
92 | Gan Kim Aun | 2019-10-11 | Data Error (Conversion) | 4-Low | Open | UAT | Ong Yei Ling | QFPay IMS Transaction Details function support to show history
93 | Gan Kim Aun | 2019-10-11 | Data Error (Conversion) | 3-Medium | Open | UAT | Ong Yei Ling | QFPay Settlmenet Report QFPS0002 - Transaction Printing Issue
94 | Gan Kim Aun | 2019-10-11 | Data Error (Conversion) | 4-Low | Open | UAT | Ong Yei Ling | QFPay IMS - Edit Merchant Info - TPA Name field is editable eventhough is grey